# Action Plan

Stage-Gated Development and Filing Plan — SurvAIve PH

Prepared in support of an Intellectual Property Rights application with the Intellectual Property Office of the Philippines (IPOPHL)

MSIT Capstone Project  |  Proponent(s): [Proponent Name(s)]  |  Adviser: [Adviser Name]  |  Date: [Defense Date]

TABLE A — FEATURE DEVELOPMENT PROGRESS BY STAGE (%)

| Tangible Feature / Design Requirement | Idea | Screen | Design | Development | Test | Launch | Post-launch | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Offline-First Local Persistence (IndexedDB) | 100% | 100% | 100% | 100% | 100% | 90% | 40% | 90% |
| Mesh Networking: BLE / Wi-Fi Direct / WebRTC | 100% | 100% | 100% | 100% | 90% | 80% | 30% | 86% |
| AI-Based Rescue Prioritization Engine | 100% | 100% | 100% | 100% | 100% | 85% | 35% | 89% |
| Intelligent Resource Allocation Engine | 100% | 100% | 100% | 100% | 90% | 80% | 30% | 86% |
| Real-Time Situational Dashboards | 100% | 100% | 100% | 100% | 100% | 90% | 40% | 90% |
| SOS & Incident Reporting Module | 100% | 100% | 100% | 100% | 100% | 95% | 45% | 91% |
| Role-Based Access (4 roles) | 100% | 100% | 100% | 100% | 100% | 90% | 40% | 90% |
| Constituent & Safety Registry | 100% | 100% | 100% | 100% | 90% | 85% | 35% | 87% |
| Opportunistic Data Sync & Conflict Resolution | 100% | 100% | 100% | 95% | 85% | 75% | 25% | 83% |
| PHP/MySQL Multi-Role Backend | 100% | 100% | 100% | 100% | 100% | 90% | 40% | 90% |

TABLE B — STAGE TASKING, OWNERSHIP, MILESTONES, AND BUDGET

| Stage | Key Tasking | Who Is Responsible | Completion Milestone | Budget | Start / End Dates |
| --- | --- | --- | --- | --- | --- |
| Idea | Problem identification, literature review, stakeholder interviews (LGU/DRRM offices), initial concept validation for an offline-first, AI-assisted disaster platform. | Proponent(s) | Approved concept paper and problem statement | PHP 5,000 | Aug 2025 – Sep 2025 |
| Screen | Feasibility study, technology stack evaluation (offline storage, mesh protocols, AI models), requirements gathering, risk and scope assessment. | Proponent(s) / Adviser | Approved project proposal and feasibility report | PHP 8,000 | Sep 2025 – Oct 2025 |
| Design | System architecture design, database schema, UI/UX wireframes, AI model design, role-based access design for 4 user roles. | Proponent(s) / Adviser | Approved system design document and prototypes | PHP 15,000 | Oct 2025 – Dec 2025 |
| Development | Implementation of offline-first PWA, mesh networking layer, AI prioritization and allocation engines, dashboards, SOS module, PHP/MySQL backend. | Proponent(s) | Functional system build (alpha/beta release) | PHP 60,000 | Jan 2026 – Apr 2026 |
| Test | Unit, integration, and field testing (offline mode, mesh relay range, AI accuracy), usability testing with simulated LGU/responder users, bug fixes. | Proponent(s) / Panel | Test report and validated, stable build | PHP 20,000 | Apr 2026 – Jun 2026 |
| Launch | Final defense, capstone pilot deployment, IPOPHL Intellectual Property Rights filing, documentation finalization. | Proponent(s) / Adviser / Panel | Successful defense, pilot go-live, and IP filing submission | PHP 12,000 | Jul 2026 – Aug 2026 |
| Post-launch | Monitoring, maintenance, user feedback collection, roadmap planning for scale-up to municipal and provincial DOST-level deployment. | Proponent(s) | Maintenance plan and scale-up roadmap | PHP 5,000 | Sep 2026 onward |

Total indicative project budget across all stages: PHP 125,000. Dates reflect the proponent's academic-term schedule and are subject to adviser and panel scheduling; figures should be replaced with confirmed values prior to formal IPOPHL submission.